## PBI
WORK MANAGEMENT PRODUCT BACKLOG ITEMS
BackLog Items | Story Point estimate | Sprint | Description | Acceptance criteria | Comments/Dependency
Discuss Project ideas and Vision | 13 | 0 | All team members should contribute and come up with a Project Idea and Vision | All team members should agree on Project Idea and its vision
Prepare and document project proposal | 8 | 0 | Prepare proposal document for the Project Idea, include StakeHolders and Product Vision | Project Proposal should clearly document Vision for Project, Problem, Proposed Solution and Stakeholders
Discuss and select tools and frameworks to be used in project | 5 | 1 | All team members should agree on technology and toolset to be used to deliver this Project. | Entire team should agree that selected tools and framework is best choice for implementing the Project
Setup skeleton web application | 8 | 1 | Setup a basic skeleton web application, with choosen framework. | Any Team member should be able to download the skeleton WebApp from Git repository to local environment and verify in local environment without any issues.
Set up Database server | 5 | 1 | Setup database server
Set up local development environment | 8 | 1 | Install and setup all tools and servers on every team members local environment. | Every team member's local DEV environment should have all selected tools and framework installed, skeleton webapp downloaded from git repository and read to begin development
create Database design for WorkPackage Tool | 8 | 1 | Create DB design and identify all Entities, attributes and relationships between entities. | All Entities, its attributes and relationship between entities should be identified. ER Diagram should also be delivered. | Usha should provide a sample WorkPackage data that stakeholder is currently using.
create scripts to populate lookup tables | 5 | 1 | Populate users and roles for BusinessUnit user, Demand management group user, Applicationgroup user. Populate DB data for ResourceTypes and their billing rates | Using DB client verify data is populated in all lookup tables
Implement userid/password based security | 13 | 1 | Use Shiro for user authentication | BusinessUnit user, Demand management group user, Application group user should be able to successfully login to the system.
Create/implement user login screen | 8 | 1 | User should be able to login to the system by entering valid credentials.
Create/configure server on AWS for the project | 8 | 1 | To demo Product increment at the end of each sprint. | User should be able to access AWS server and login to WorkManagement application.
Configure and deploy application on AWS server for demo | 8 | 1
Create User landing/dashboard page | 13 | 2 | After successful login, user should be displayed with dashboard/home page | Different home page for each user role should be displayed.
Create/implement screen to create Work package | 13 | 2 | As a Demand management group user I should be able to create WorkPackage and capture all details relaed to to the WorkPackage like Title, Description, Expected Live Date, impacted applications. | WorkPackage creation should be successful. WorkRequest for each impacted application should be successfully created.
Create/Implement screen to add Impacted applications to Workpackage | 3 | 2 | As a Demand management group user I should be able to add impacted applications to the WorkPackage.
Add functionality to create WorkRequests for each impacted application when Work package is saved | 8 | 2 | When a Demand management user creates WorkPackage, WorkRequest for every impacted application of the WorkPackage should be created.
Screen to view existing Work package details | 8 | 2 | As a Demand management group user I should be able to view existing WorkPackage details like Title, Description, Expected Live Date, impacted applications. I should also be able to view assigned WorkRequests, the status of each WorkRequest and effort for those WorkRequests if available. | User should be able to successfully view WorkPackage details of an exisitng WorkPackage
WorkPackage View Screen : Implement feature to view all Activities/Assigned ResourceType/Effort for each WorkRequest | 13 | 2
Workpackage list screen to capture list of Workpackages | 5 | 2 | As a BusinessUnit user/Demand management group user I should be able to view all WorkPackages | Demand management group user and Business unit user should be able to view all WorkPackages
Workrequests list screen to capture list of Workrequests | 5 | 2 | As a ApplicationGroup user I should be able to view all WorkRequests assigned to me. | Application group user should be able to view all WorkRequests assigned to him/her.
Create/implement screen to capture Activiies for a Work request | 8 | 3 | As a ApplicationGroup user I should be able to create multiple activities for the Work Request and capture all details related to to the Activity. I should be able to enter Activity Description, assign type of resource (Dev/Architect/BA/DBA), hours required to complete the activity. I should also be able to enter assumptions against each activity.ApplicationGroup user can update status of the Work Request to "Completed" | An ApplicationGroup user should be able to 1. create Activities for a WorkRequest. 2. Assign Resource Type to an Activity 3. Assign effort for each ResourceType 4. Enter Comments/Justification against each activity. 5. Successfully save
WorkRequest screen : Add functionality to add/associate ResourceType with each activity. | 5 | 3
WorkRequest screen : Add functionality to add effort estimate as man hours for each activity/ResourceType. | 5 | 3
WorkRequest screen : Add functionality to add comments/justification for each activity/ResourceType. | 5 | 3
WorkRequest screen : When WorkRequest is saved, Compute total estimate and Cost for each Work Request | 5 | 3 | Every time activities for a WorkRequest is created/updated, compute total cost for the WorkRequest by aggregating total number of hours for each actiivity under the WorkRequest and billing rate for each assigned resource type. System should store this cost value against WorkRequest item. | When WorkRequest is saved, Cost for the WorkRequest should be saved in Database against WorkRequest entity.
Screen to view existing WorkRequest details | 8 | 3 | As a ApplicationGroup user I should be able to view all Activities for a WorkRequest. | All Activities for a WorkRequet should be displayed
Update status of WorkRequest | 5 | 3 | As a Demand management group user I should be able to update status of WorkRequest to Approved/Cancelled/Re-Open | WorkRequest status update should be successful. Possible change of status are 1. Submitted to Approved 2. Submitted to Cancelled 3. Submitted to Re-Open
Update status of WorkPackage | 5 | 3 | As a BusinessUnit user I should be able to update status of WorkPackage to Approved/Cancelled/Re-Open | WorkPackage status update should be successful. Possible change of status are 1. Submitted to Approved 2. Submitted to Cancelled 3. Submitted to Re-Open
Implement UserAuthorization | 8 | 3 | Restrict user navigation to only those pages for which logged in user has access. Ex : Applicationgroup User cannot view WorkPackage screen. | Application group user should only view WorkRequest assigned to him/her. Application group user should not be able to view WorkPackage screen
Create/Implement screen to search WorkPackage | 8 | 3 | As a BusinessUnit user I should be able to search WorkPackages by date or status (opened/approved/cancelled) or a combination of these | All Workpackages satisfying the search criteria should be displayed
Create/Implement screen to search WorkRequests | 8 | 3 | As a Demand management group user I should be able to search WorkRequests by date or application or status (opened/approved/cancelled) or a combination of these | All WorkRequests satisfying the search criteria should be displayed
Write high level usage document for application | 5 | 3 | As a application end user I need a high level application usage document for user training | End user should be able to navigate and access the application with the help of this document
RELEASE MARKER
Create/Implement screen to create Roles | 5 | 4 | As an admin user I should be able to create Roles | Admin user should be able to create new roles in system
Create/Implement screen to update Roles | 5 | 4 | As an admin user I should be able to update Roles | Admin user should be able to update exising roles in application
Create/Implement list screen to view Roles | 5 | 4 | As an admin user I should be able to view list of available Roles | Admin user should be able to view list roles in system
Create/Implement screen to create Users | 5 | 4 | As an admin user I should be able to create Users | Admin user should be able to create new Users for system
Create/Implement screen to update Users | 5 | 4 | As an admin user I should be able to update Users | Admin user should be able to modify existing users in system
Create/Implement list screen to view Users | 5 | 4 | As an admin user I should be able to view list of available Users | Admin user should be able to view list of users along with their status in system
Create/Implement screen to assign Roles to Users | 5 | 4 | As an admin I should be able to assign role(s) to Users | Admin user should be able to assign /unassign roles to user
Create/Implement screen to create Resource Types | 5 | 4 | As an admin user I should be able to create ResourceTypes (Developer, DBA, BA, QA). I should also be able to assign a billing rate. | Admin user should be able to add new resource type in system using some UI interface
Create/Implement screen to update Resource Types | 5 | 4 | As an admin user I should be able to update ResourceTypes (Developer, DBA, BA, QA). I should also be able to update billing rate. | Admin user should be able to modify resource type in system using some UI interface
Create/Implement list screen to view Resource Types | 5 | 4 | As an admin user I should be able to view list of ResourceTypes (Developer, DBA, BA, QA). I should also be able to view their Billing rate. | Admin user should be able to associate rates with resource types using some UI interface
Create /implement screen to add new Applications | 5 | 4 | As an admin user I should be able to add new Application information. | Admin user should be able to create new applications in system using UI interface
Create/implement screen to update existing Applications | 5 | 4 | As an admin user I should be able to update Application information. | Admin user should be able to update exisitng applications information in system using UI internface
Create/implement screen to associte ApplicationGroup user with Applications. | 5 | 4 | As an admin user I should be able to associate ApplicationGroup user to an Application. | Admin user should be able to associate user with ApplicationGroup role to the application
Edit screen to update existing Work package details | 13 | 5 | As a Demand management group user I should be able to edit existing WorkPackage and update details relaed to to the WorkPackage like Title, Description, Expected Live Date, impacted applications. The work package once submitted triggers multiple “work requests” by application and dispatches to the individual application contacts. | Demand management group user should be able to edit information about existing work package
Add functionality to send email notification to Impacted Application's contact when Workpackage is saved. | 8 | 5 | As a Demand management group user, when I save a WorkPackage after adding the Impacted application details, an email notification message should be sent to the ApplicationContact user. | Upon saving of WorkPackage the application should already send email notification for each WorkRequest to the user associate with Application
Edit screen to update existing WorkRequest details | 13 | 5 | As a ApplicationGroup user I should be able to edit existing Activity and update details relaed to the Activity like Description, changed assigned resource type, update hours, status of the activity. ApplicationGroup user can update status of the Work Request to "Completed". | Application group user should be able to edit information about existing work request